## Sheet1
ID | Risk Description | Likelihood | Impact | Mitigation Strategy
1 | Scope creep due to unclear requirements | High | High | Define scope clearly and conduct stakeholder reviews
2 | Delay in development due to resource unavailability | Medium | High | Have backup developers and manage buffer time
3 | Inadequate testing leads to bugs in production | High | Medium | Ensure thorough test cases and code reviews