## Sheet1
Phase | Start Week | End Week | Duration (Weeks)
Requirements Gathering | 1 | 2 | 2
Design | 3 | 4 | 2
Development | 5 | 7 | 3
Testing | 8 | 9 | 2
Deployment | 10 | 10 | 1
Retrospective | 11 | 12 | 2